## Product Backlog
Actual Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint1 | Sprint1 | US-01 | Setup Streamlit app structure and navigation ¦ | MUST HAVE | None | KANNAN S | 3- Completed
Sprint1 | Sprint1 | US-02 | Load healthcare dataset from Excel files | MUST HAVE | US-01 | KANNAN S | 3- Completed
Sprint1 | Sprint1 | US-03 | Implement KPI cards for key metrics | MUST HAVE | US-02 | KANNAN S | 3- Completed
Sprint1 | Sprint1 | US-04 | Build patient flow trend chart | SHOULD HAVE | US-02 | KANNAN S | 3- Completed
Sprint2 | Sprint2 | US-05 | Develop Patient Demographics & Demand Analysis page | MUST HAVE | US-02 | KANNAN S | 3- Completed
Sprint2 | Sprint2 | US-06 | Develop Clinical & Disease Intelligence page | MUST HAVE | US-06 | KANNAN S | 3- Completed
Sprint2 | Sprint2 | US-07 | Develop Operational Efficiency & Capacity page | MUST HAVE | US-07 | KANNAN S | 3- Completed
Sprint3 | Sprint3 | US-08 | Implement Staffing & Resource Optimization page | MUST HAVE | US-02 | KANNAN S | 3- Completed
Sprint3 | Sprint3 | US-09 | Add global filters for date, department, demographics | SHOULD HAVE | US-05, US-06 | KANNAN S | 3- Completed
Sprint3 | Sprint3 | US-10 | Implement dark/light theme toggle | COULD HAVE | US-01 | KANNAN S | 3- Completed
Sprint3 | Sprint3 | US-11 | Optimize performance using caching | SHOULD HAVE | US-02 | KANNAN S | 3- Completed
Sprint3 | Sprint3 | US-12 | Bug fixes and UI refinements | MUST HAVE | US-03, US-04, US-05 | KANNAN S | 3- Completed
Sprint3 | Sprint3 | US-13 | Implement Operational Alerts for key hospital KPIs | MUST HAVE | US-02, US-04 | KANNAN S | 3- Completed
Sprint3 | Sprint3 | US-14 | Build Patient Journey Timeline visualization | SHOULD HAVE | US-02, US-05 | KANNAN S | 3- Completed
Sprint3 | Sprint3 | US-15 | Develop Capacity Planning Simulator for beds and staff | MUST HAVE | US-04, US-07 | KANNAN S | 3- Completed
Sprint3 | Sprint3 | US-16 | Add PDF report generation for selected dashboard charts | COULD HAVE | US-01, US-02 | KANNAN S | 3- Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 51 | 24 | 21 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-01 | TASK-001 | Explore multiple healthcare datasets | 2026-02-02 | 2026-02-04 | Everyone | Data Gathering | Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | TASK-002 | Finalize one dataset after comparision | 2026-02-05 | 2026-02-06 | Everyone | Data Gathering | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | TASK-003 | Define dashboard pages, KPIs, and workflow | 2026-02-07 | 2026-02-10 | Everyone | Planning | Completed | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | TASK-004 | Assign pages to interns | 2026-02-10 | 2026-02-11 | Everyone | Planning | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
US-01 | TASK-005 | Develop Executive Overview page | 2026-02-12 | 2026-02-13 | Niyati Bansal | Coding | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | TASK-006 | Make final changes in Executive Overview page | 2026-02-13 | 2026-02-14 | Ameesha Gade | Coding | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | TASK-007 | Develop Patient Demographics & Demand Analysis page | 2026-02-12 | 2026-02-13 | Priyanshi Kunte | Coding | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | TASK-008 | Edit features and charts in Page 2 | 2026-02-13 | 2026-02-14 | Divya Jaiswal | Coding | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | TASK-009 | Made final changes in page 2 | 2026-02-13 | 2026-02-14 | Sheela Priyadarshini | Coding | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | TASK-010 | Develop Clinical and Disease Intelliegence Page | 2026-02-13 | 2026-02-14 | Dongiri Tabassum | Coding | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | TASK-011 | Made final changes in page 3 | 2026-02-14 | 2026-02-15 | Kanika Priya | Coding | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | TASK-012 | Develop Operational Efficeincy & Capacity page | 2026-02-13 | 2026-02-14 | Clarisha Pinto | Coding | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | TASK-013 | Add required charts in page 4 | 2026-02-14 | 2026-02-15 | Eekshita Maram | Coding | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | TASK-014 | Made final changes in page 4 | 2026-02-15 | 2026-02-16 | Rounak Kumar | Coding | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | TASK-015 | Develop Staffing & Resource Optimization page | 2026-02-14 | 2026-02-15 | Kannan | Coding | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | TASK-016 | Made final changes in page 5 | 2026-02-15 | 2026-02-16 | Meghana | Coding | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG
US-12 | TASK-017 | Fix issues based on mentor feedback | 2026-02-17 | 2026-02-20 | Everyone | Coding | Completed | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | TASK-018 | Add global filters | 2026-02-18 | 2026-02-20 | Everyone | Coding | Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | TASK-019 | Implement dark/light theme toggle | 2026-02-19 | 2026-02-19 | Everyone | Coding | Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | TASK-020 | Optimize performance using caching | 2026-02-20 | 2026-02-20 | Everyone | Coding | Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-13 | TASK-021 | Implement operational alerts | 2026-02-21 | 2026-02-22 | Everyone | Coding | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-14 | TASK-022 | Build patient journey timeline | 2026-02-22 | 2026-02-23 | Everyone | Coding | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-15 | TASK-023 | Develop capacity planning simulator | 2026-02-23 | 2026-02-24 | Everyone | Coding | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-16 | TASK-024 | Add PDF report geenration | 2026-02-24 | 2026-02-24 | Everyone | Coding | Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABYLGvqXg Please enter the dates in either of these formats (2024-11-14 13:03:52) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABYLGvqXI Please enter the dates in either of these formats (2024-11-14 13:03:52) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABYLGvqXQ Sumeet Kumar Barua08 (2024-11-14 13:03:52) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABYLHdiCk Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABYLGvqX4 Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABYLGvqXU Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABYLGvqXs Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABYLHdiCs Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABYLGvqXY Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABYLGvqXo Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABYLGvqXw Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABYLGvqX8 Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABYLGvqXE Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABYLGvqXc Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABYLHdiCo Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABYLGvqX0 Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABYLGvqXk Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 14 work

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | S1 | 2026-02-02 | 2026-02-11 | KANNAN S | Shortlisting datasets using clear criteria | Randmly switching datasets without validation | Team discussions before final decisions | Finalized a single healthcare dataset and documented columns
2 | S2 | 2026-02-12 | 2026-02-16 | KANNAN S | Breaking dashboard pages into smaller implementation tasks | Waiting for others before starting own page | Regular code commits and peer reviews | Implemented page-wise task checklist
3 | S3 | 2026-02-17 | 2026-02-24 | KANNAN S | Fixing issues immediately after mentor feedback | Deferring bug fixes to the end of the sprint | Incremental improvements and UI polish | Resolved review comments promptly and completed dashboard features

## Stand up meeting
Sprint | Day | Impediments | Action Taken
S1 | Day3 | Lack of clarity while selecting the final datasets | Conducted team discussion and compared multiple datasets
S1 | Day6 | Confusion about dashboard page flow and KPIs | Finalized page structure after mentor discussion
S2 | Day11 | Difficulty in aligning charts with datasets columns | Cleaned and mapped dataset columns before implementation
S3 | Day17 | Issues found during mentor review | Fixed issues immediately and retested affected pages
S3 | Day20 | UI inconsistency and filter-related bugs | Refined UI components and stabilized filter logic
S3 | Day23 | Final documentation and packaging delays | Dedicated time slots to complete Agile documentation and final checks